## Gantt Chart
TASKS | Start Date | End Date | FEBRUARY | [8 empty] | MARCH | [30 empty] | APRIL
|  |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Phase I - Login
Login UI Template | 02/20/2019 | 02/24/2019 | bar: FEBRUARY 20 to FEBRUARY 24
Login backend | 02/24/2019 | 02/28/2019 | bar: FEBRUARY 24 to FEBRUARY 28
Input Validation and authentication | 2019-01-03 | 2019-03-03 | bar: MARCH 1 to MARCH 3
Phase II - Admin Portal
Dashboard | 03/04/2019 | 03/11/2019 | bar: MARCH 4 to MARCH 11
Video List Page | 03/11 /2019 | 03/18/2019 | bar: MARCH 11 to MARCH 18
Evaluation functions | 03/18/2019 | 03/25/2019 | bar: MARCH 18 to MARCH 25
Student Info page | 03/25/2019 | 03/27/2019 | bar: MARCH 25 to MARCH 27
Activity Logs | 03/27/2019 | 03/28/2019 | bar: MARCH 27 to MARCH 28
Account Settings | 03/28/2019 | 03/30/2019 | bar: MARCH 28 to MARCH 30
Report Page | 03/30/2019 | 04/06/2019 | bar: MARCH 30 to APRIL 6
Phase III - User Portal
Dashboard | 03/04/2019 | 03/11/2019 | bar: MARCH 4 to MARCH 11
Video List Page | 03/11/2019 | 03/16/2019 | bar: MARCH 11 to MARCH 16
Evaluation History Page | 03/16/2019 | 03/20/2019 | bar: MARCH 16 to MARCH 20
Account Settings | 03/20/2019 | 03/22/2019 | bar: MARCH 20 to MARCH 22
Phase IV - User Portal
Storyboard | 02/20/2019 | 02/28/2019 | bar: FEBRUARY 20 to FEBRUARY 28
Animation 1 | 02/28/2019 | 03/14/2019 | bar: FEBRUARY 28 to MARCH 14
Animation 2 | 03/14/2019 | 03/28/2019 | bar: MARCH 14 to MARCH 28
Phase V - Integration
Integration | 04/06/2019 | 04/17/2019 | bar: APRIL 6 to APRIL 17
COLOR LEGEND
Completed
In Progress
Not Yet Started
Overdue